## Shift Giving App Features
Shift Giving App Features
Features: Phase 1 | Notes | Priority | Status
Simple campaigns | With customizable pages | High | In Progress
Rich storytelling capabilites | With donor engagement and thank you emails | High | In Progress
Donor portal & login | With recurring donation options | High | In Progress
Organization online sign up |  | High | In Progress
Payment system | Including ACH payment to organizations | High | In Progress
Push notifications |  | High | In Progress
Multi tenancy |  | High | In Progress
Features: Phase 2 | Notes | Priority | Status
Tax deductible tracking | Including "offline" donations | Medium | Not Started
Advaced giving campaigns | Including urgent call to actions to donors | Medium | Not Started
Offline campaign giving
Media library | With content management | Medium | Not Started
Donor dashboard and management | With reporting capabilities | Medium | Not Started
Advaced payment options | Including Google and Apple Pay | Medium | Not Started
Features: Phase 3 | Notes | Priority | Status
Payroll deduction |  | Low | Not Started
Recommendation engine |  | Low | Not Started
Gamified options |  | Low | Not Started
Advanced billing |  | Low | Not Started
Features: Phase 4 | Notes | Priority | Status
Peer to Peer campaign pages |  | Low | Not Started
Multi currency languages |  | Low | Not Started
Features: Phase 5 | Notes | Priority | Status
Event mangement | With ticketing & auction options | Low | Not Started
Tribute/memorial donation options |  | Low | Not Started
Grant tracking and management |  | Low | Not Started
Company matching capabilities |  | Low | Not Started
Features: Phase 6 | Notes | Priority | Status
Volunteer coordination |  | Low | Not Started

## Comments (hidden)
Strategic Objective |  | Program / Initiative | Comments
Develop New Business Models and Innovative Products and Services | 2 | Asset Evaluation | On hold pending completion of budget reviews
| 3 | Innovative Products / Services
| 3a | Pharmacy Concierge | ~880 scripts filled to date (76 last week). Humana requested add'l info. Cigna denied application for non-Mcre b/c not a retail pharmacy. Rolled out hospital wide at JDHC and MRH - working on increasing demand. 2.18% fill rate (versus target of 5%), sponsor mtg 2/28
| 3b | CMS Bundled Payments | Care model redesign recommendations presented 2/18; draft gain sharing model complete and under Legal review, physician participation agreement under development, comments provided on CMS Quality metrics and scorecard development underway, communications plan in under Lead / Sponsor review, beneficiary communications pending CMS guidance
| 4 | Project Everglades | Little movement on LMHS side.
Create Clinically Integrated Delivery System and Launch Progressive Care Models | 3 | Clinical Integration | Will be removed from Dashboard post March 28th Board meeting
| 3a | Operations | Operations manager interviews underway
| 3b | Credentialing and Peer Review | Approved physician orientation materials
| 3c | Finance and Contracting | Shared savings methodology approved by F&C, slated for approval at March Board meeting
| 3d | Quality and Information Technology | Scorecard approved
| 4 | Physician Alignment Strategies
| 4a | Primary Care | PCPs developing business plan and proposal with Holland and Knight to present to the District, Kim to follow up with Maria Currier to develop timeline; expect proposal to be complete by end of March
| 4b | Surgical Specialists | Surgeons: 4 in contracting, 2 in DD, 2 in discussion; Ortho: no progress; ENT: 2 fully implemented, 2 in discussion
| 4c | Medical Specialists | Cardiology: reps from 2 key groups meeting to define go-forward strategy; Neuro: Dr. Shebert + 4 in discussions, if unsuccessful, will pursue recruitment; OB/GYN: providing recruitment assistance; Pysiatry: DD being evaluated
| 4d | ED Coverage (Hospitalists & Specialists) | Proceeding towards closed hybrid model, proceeding with assessment of ED coverage contract, RFI to be issued 3/8
Enhance Value and Implement Cost Reduction | 5 | Clinical Effectiveness
| 5a | VBP, Readmissions and LOS | Team working on defining staffing requirements for rolling out strategies to additional diagnoses, also defining KPIs and tracking process, return to Executive Staff 3/8
| 5b | Pharmacy Antibiotic Stewardship | Phase 2 timeline complete, initial focus on Criteria Based Order sets for high cost ,inappropriately used antibiotics
| 6 | Cost Reduction
| 6a | Task Execution | Total reported savings to date is $46.7M vs. a $48.9M target. Complete (95.5%). Phase 2 still to be defined - target to be set based on AHCA comparison
| 6b | Staffing Ph 1: Optimize Nursing | Have achieved $4.6 million of target $4.9M through pay period ending 1/12/13; JDHC, MHM, MRHS have exceeded plan; MHW 94%, MHP 89%, MHR 43%
| 6c | Staffing Ph 2: IQS - MRH | Reported $3 million implemented (some double counting) + $1.4 million planned at 90 day summation, complete, remove?
| 6d | Staffing Ph 3: RCT - MHW | Monitoring of execution beginning this week, will report monthly
| 6e | Staffing Ph 4: RCT - MHM | Data collection and review underway
| 6f | Revise HR Benefit - Phase 1 | 2012 baseline will be established in April and savings monitored quarterly in conjunction with MHN process
| 6f | Human Resources Reorganization | Some slippage in interim milestones dates: posting leadership positions, alignment on which Employee Health functions will be centralized, selecting HRIS vendor (unsatisfactory ref check with Cleveland Clinic, follow up with Geisinger - site visit 2/26)
| 7 | ICD10
| 7a | HIM / CDMP | Looking to contract to hire for workstream lead, clinical documentation project at-risk for data, timeline and budget
| 7b | Finance
| 7c | Clinical Operations
| 7d | Training
| 7e | IT | Issue with 3M CAC Encoder failure. Solution in beta testing. Questions remain re: workstream lead allocation
| 7f | RCM
| 7g | Physician
| 7h | MIH
| 7j | Project Management | Reported as "at-risk" due to admin assistant resource
| 8 | Epic
| 8a | EHR Ambulatory
| 8b | Epic Inpatient Clinicals (EIC) | EIC at MPH, MWH, UCC, Manor – Go live 4/20/2013
| 8b | Radiant and Cupid | Radiant and Cupid – Start 5/1/2013 , Target Go-Live 7/13/2014: All hospitals, Training analyst and pre-planning has already begun
| 8b | Upgrade to 2012 | Upgrade to 2012 – Start 6/1/2013, Target Go-Live Nov 2013: All hospitals
| 8c | Standardization of Order Sets | 616 standard order sets completely implemented
| 9 | EHR Donation Program | EHR- 128 practices signed with 218 providers. 30 practices interested with 59 providers. 95% of 230 goal by end of FY2013 HIE-26 practices LIVE with 35 providers and 139 named users.