## feature estimator v2
Item | Software Development (in days) | Native App Development (in days) | Testing/Revisions (in days) | Total Time (in days) | Notes
Total Days | 163 | 0 | 0 | 163
| 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0
Feature 6 | 0 | 0 | 0 | 0
Feature 7 | 0 | 0 | 0 | 0
Feature 8 | 0 | 0 | 0 | 0
Feature 9 | 0 | 0 | 0 | 0
Feature 10 | 0 | 0 | 0 | 0
Feature 11 | 0 | 0 | 0 | 0
Feature 12 | 0 | 0 | 0 | 0
Feature 13 | 0 | 0 | 0 | 0
Feature 14 | 0 | 0 | 0 | 0
Feature 15 | 0 | 0 | 0 | 0
|  |  | Total Days | 163 | 1304
Who | Role | Days Needed | FTE percent | Cost
Rails | Software Engineer | 163 | 75% | 146700
Rails | Software Engineer | 163 | 100% | 195600
React Native | Software Engineer | 163 | 100% | 195600
Chris | UI UX | 163 | 50% | 97800
Cliff/Cathy | Delivery Lead | 163 | 50% | 97800
| -Select- | 163 | 100% | 0
| -Select- | 163 | 25% | 0
| -Select- | 163 | 25% | 0
| -Select- | 163 | 25% | 0
| -Select- | 163 | 25% | 0
Project completion in weeks | 33
Value Add (in Dollars) | 5000
Dollar already invested | 10000
Total Project Cost | 748500

## data
Item Code | Rate | FTE |  | Allocations Percents
-Select- | 0 | A year | 2080 | 25%
Account Lead | 150 | FTE hours a week | 40 | 50%
Delivery Lead | 150 | FTE hours a day | 8 | 75%
Leadership | 175 | A FTE a week (in days) | 5 | 100%
Native App Enginner | 150
Software Engineer | 150
UI UX | 150
Sales | 0%

## OLD - fixed (hidden)
Project Name
Silent Partner Job Number
Team
Date
Item | Business Analyst (hours) | Wireframe (hours) | Designs (hours) | Development (hours) | Peer Review | Revisions | Testing | Management | Planning/Meetings | Dev Effort | Total Effort | Notes
Feature 1 | 8 | 0 | 0 | 16 | 0.75 | 2.5 | 2.5 | 6.5 | 3.5 | 19.25 | 39.75
Feature 2 | 2 | 8 | 10 | 12 | 0.5 | 4.5 | 1.75 | 11.75 | 1.75 | 17 | 50.25
Feature 3 | 3 | 14 | 16 | 18 | 1 | 7.25 | 2.75 | 18.5 | 2.75 | 26.25 | 80.25
Feature 4 | 4 | 4 | 4 | 4 | 0.25 | 1.75 | 0.5 | 5.5 | 0.5 | 6 | 20.5
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 17 | 26 | 30 | 50 | 2.5 | 16 | 7.5 | 42.25 | 8.5 | 68.5 | 190.75
Tool Box
Peer Review | 5%
Revisions | 15%
Testing | 15%
Management | 30%
Planning | 15%
Hours already invested | 100
Launch checklist | 12
Summary | Feature Effort (in hours) | Priority | Mandatory | Value Modifier (+/- hours) | Cost
Feature 1 | 39.75 | 1 | Y |  | 4968.75
Feature 2 | 50.25 | 2 | Y |  | 6281.25
Feature 3 | 80.25 | 3 | N |  | 10031.25
Feature 4 | 20.5 |  | Y |  | 2562.5
Hours already invested |  |  |  |  | 12500
Launch checklist |  |  |  |  | 1500
Project costs with only mandatory items | 27812.5
Total Project Cost | 37843.75

## OLD - ranged (hidden)
Project
Silent Partner Job Number
Team
Date
Item | Business Analyst (optimistic) | Business Analyst (pessimistic) | Wireframes (optimistic) | Wireframes (pessimistic) | Design (optimisitc) | Design (pessimistic) | Dev Effort (optimistic) | Dev Effort (pessimistic) | Total Dev Effort (optimistic) | Total Dev Effort (pessimistic) | Total Effort (optimistic) | Total Effort (pessimistic) | Notes | Peer Review (optimistic) | Revisions (optimistic) | Testing (optimistic) | Management (optimistic) | Planning/Meetings (optimistic) | Peer Review (pessmisitic) | Revisions (pessmisitic) | Testing (pessmisitic) | Management (pessmisitic) | Planning/Meetings (pessmisitic) | Unhide to see support totals
Feature 1 | 2 | 4 | 2 | 4 | 6 | 8 | 10 | 12 | 22.75 | 33.5 | 32 | 34.5 |  | 0.5 | 2.75 | 1.5 | 6.75 | 0.5 | 0.5 | 7.25 | 1.75 | 10 | 3
Feature 2 | 6 | 8 | 14 | 16 | 18 | 20 | 22 | 24 | 66.25 | 82.75 | 93.25 | 119 |  | 1 | 8 | 3.25 | 20 | 1 | 1.25 | 18 | 3.5 | 24.75 | 3.5
Feature 3 | 10 | 12 | 26 | 28 | 30 | 32 | 34 | 36 | 110.25 | 132 | 155 | 189 |  | 1.75 | 13.5 | 5 | 33 | 1.75 | 1.75 | 28.75 | 5.5 | 39.5 | 5.5
[9 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 18 | 24 | 42 | 48 | 54 | 60 | 66 | 72 | 199.25 | 248.25 | 280.25 | 342.5 | 0 | 3.25 | 24.25 | 9.75 | 59.75 | 3.25 | 3.5 | 54 | 10.75 | 74.25 | 12
Tool Box
Peer Review | 5%
Testing | 15%
Revisions | 15%
Management | 30%
Planning | 15%
Hours already invested | 100
Launch checklist | 12
Summary | Optimistic Hours | Pessimistic Hours | Priority | Mandatory | Value Modifier (+/- hours) | Low Cost | High Cost
Feature 1 | 32 | 34.5 | 1 | Y |  | 4000 | 4312.5
Feature 2 | 93.25 | 119 | 2 | Y |  | 11656.25 | 14875
Feature 3 | 155 | 189 | 3 | Y |  | 19375 | 23625
Hours already invested |  |  |  | Y |  | 12500 | 12500
Launch checklist |  |  |  | Y |  | 1500 | 1500
Project costs with only mandatory items | $49031.25 - $56812.5
Project total | $49031.25- $56812.5

## OLD - pm - fixed (hidden)
Project
Silent Partner Job Number
Team
Date
Item | Business Analyst (hours) | Wireframe (hours) | Design (hours) | Effort (hours) | Peer Review | Revisions | Testing | Management | Planning/Meetings | Dev Effort | Total Effort | Notes
Deliverable 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 4.5
Deliverable 2 | 2 | 8 | 10 | 12 | 0.5 | 3 | 1.25 | 7 | 2 | 33.5 | 45.75
Delvierable 3 | 3 | 14 | 16 | 18 | 1 | 4.75 | 1.75 | 11 | 3.25 | 53.75 | 72.75
Deliverable 4 | 4 | 20 | 22 | 24 | 1.25 | 6.5 | 2.5 | 15.25 | 4.25 | 73.75 | 99.75
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 13 | 42 | 48 | 54 | 2.75 | 14.25 | 5.5 | 33.25 | 10 | 161 | 222.75
Tool Box
Peer Review | 5%
Revisions | 10%
Testing | 10%
Management | 20%
Planning | 15%
Shift Dev Rate to PM | 115
Shift Accout Service Rate to PM, | 105
PM to client dev rate | 125
PM to client account service rate | 125
Hours already invested | 50
Launch checklist | 12
Summary | Total Effort (hour) | Priority | Mandatory | Cost to PM | Cost to PM Client
Deliverable 1 | 4.5 | 1 | Y | 472.5 | 562.5
Deliverable 2 | 45.75 | 2 | Y | 4958.75 | 5718.75
Delvierable 3 | 72.75 | 3 | N | 7876.25 | 9093.75
Deliverable 4 | 99.75 | 4 | Y | 10791.25 | 12468.75
Hours already invested |  |  |  | 5250 | 6250
Launch checklist |  |  |  | 1260 | 1500
Project costs with only mandatory items | 22732.5
Total Project Cost at Shift Rate | 30608.75
Total Project Cost to PM's Client | 35593.75

## pm - ranged - DEPRECATED (hidden)
Project
Silent Partner Job Number
Team
Date
Item | Wireframes (optimistic) | Wireframes (pessimistic) | Design (optimisitc) | Design (pessimistic) | Effort (optimistic) | Effort (pessimistic) | Dev Effort (optimistic) | Dev Effort (pessimistic) | Total Effort (optimistic) | Total Effort (pessimistic) | Notes |  | Peer Review (low) | Revisions (low) | Testing (low) | Management (low) | Planning/Meetings (low) | Peer Review (high) | Revisions (high) | Testing (high) | Management (high) | Planning/Meetings (high) | Unhide to see support totals
Deliverable 1 | 2 | 4 | 6 | 8 | 10 | 12 | 13.25 | 18.5 | 20.5 | 25.75 |  |  | 0.5 | 1.75 | 1 | 6.75 | 0.5 | 0.5 | 4.75 | 1.25 | 6 | 1.25
Deliverable 2 | 14 | 16 | 18 | 20 | 22 | 24 | 30.75 | 32.5 | 49.25 | 48.75 |  |  | 1 | 5.5 | 2.25 | 17.25 | 1.25 | 1.25 | 4.75 | 2.5 | 13.75 | 2.5
Deliverable 3 | 26 | 28 | 30 | 32 | 34 | 36 | 48.25 | 48.5 | 78 | 73.75 |  |  | 1.75 | 9 | 3.5 | 28 | 1.75 | 1.75 | 7.25 | 3.5 | 21.75 | 3.5
[7 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  |  | 66 | 72 | 92.25 | 99.5 | 147.75 | 148.25 | 0 | 0 | 3.25 | 16.25 | 6.75 | 52 | 3.5 | 3.5 | 16.75 | 7.25 | 41.5 | 7.25
Tool Box
Peer Review | 5%
Testing | 10%
Revisions | 10%
Management | 20%
Planning | 10%
Work hours in the day | 6
Shift Dev Rate to PM | 115
Shift Accout Service Rate to PM, | 105
PM to client dev rate | 125
PM to client account service rate | 125
Hours already invested | 50
Launch checklist | 12
Summary | Optimistic Days | Pessimistic Days | Priority | Mandatory | Low cost to PM | Low cost to PM client | High cost to PM | High cost to PM client
Deliverable 1 | 3 | 4 | 1 | Y | 3115 | 3562.5 | 4136.25 | 4718.75
Deliverable 2 | 6 | 6 | 2 | Y | 8816.25 | 10156.25 | 9198.75 | 10593.75
Deliverable 3 | 9 | 9 | 3 | N | 14517.5 | 16750 | 14493.75 | 16718.75
Y
Hours already invested |  |  |  |  | 5250 | 6250
Launch checklist |  |  |  |  | 1260 | 1500
Project duration in days (assumes 1 dev) | 18-19
Low project costs with only mandatory items (cost to PM) | $18441.25
Low project costs with mantory items (cost to PM client) | $21468.75
Low project total (cost to PM) | 32958.75
Low project total (cost to PM client) | 38218.75
High project costs wtih only mandatory items (cost to PM) | $19845
High project costs with only mandatory items (cost to PM client) | $23062.5
High proejct total (cost to PM) | 34338.75
High project cost (cost to PM client) | 39781.25

## changelog
Version | Change Log
v2.2 | adjusted caluclations for hours under a week, added sales rate m/u
v2.1 | added FTE calculator
v2.0 | added new titles, new rates, simplifyed
v1.4 | i have updated the budget estimate! here’s what I added on the fixed tab a) added a column for devin b) fixed dev effort sums to include wireframe and design c) fixed the management summing d) removed duration from summary, added Feature Effort in hours e) fixed the project cost summary at the bottom 2) fixed the default PM rates 3) upodated ranged sheet 4) hid PM - ranged sheet due to lack of use
v1.3 | Added wireframe and design columns to all sheets, copy edits
v1.2 | Added value modifer to fixed and ranged estimators
v1.1 | Addressed incorrect with on Fixed Sheet with testing and revisions
v1.0 | Initial. Uploaded to Shift Templates in Google Sheets.

## feature estimator (hidden)
Project Name
Silent Partner Job Number
Team
Date
Item | Software Development | Native App Development |  |  | UI/UX/Designs | Delviery Lead | Account Lead | Tech Lead | Leadership | Total Effort | Notes
Feature 1 | 8 |  |  |  | 4 | 2 | 2 | 0.75 | 0.75 | 17.5
Feature 2 | 8 |  |  |  | 4 | 2 | 2 | 0.75 | 0.75 | 17.5
Feature 3 | 8 |  |  |  | 4 | 2 | 2 | 0.75 | 0.75 | 17.5
Feature 4 | 8 |  |  |  | 4 | 2 | 2 | 0.75 | 0.75 | 17.5
Feature 5 | 8 |  |  |  | 4 | 2 | 2 | 0.75 | 0.75 | 17.5
Feature 6 | 8 |  |  |  | 4 | 2 | 2 | 0.75 | 0.75 | 17.5
Feature 7 | 8 |  |  |  | 4 | 2 | 2 | 0.75 | 0.75 | 17.5
Feature 8 | 8 |  |  |  | 4 | 2 | 2 | 0.75 | 0.75 | 17.5
Feature 9 | 8 |  |  |  | 4 | 2 | 2 | 0.75 | 0.75 | 17.5
Feature 10 | 8 |  |  |  | 4 | 2 | 2 | 0.75 | 0.75 | 17.5
Feature 11 | 8 |  |  |  | 4 | 2 | 2 | 0.75 | 0.75 | 17.5
Feature 12 | 8 |  |  |  | 4 | 2 | 2 | 0.75 | 0.75 | 17.5
Feature 13 | 8 |  |  |  | 4 | 2 | 2 | 0.75 | 0.75 | 17.5
Feature 14 | 8 |  |  |  | 4 | 2 | 2 | 0.75 | 0.75 | 17.5
Feature 15 | 8 |  |  |  | 4 | 2 | 2 | 0.75 | 0.75 | 17.5
Feature 16 | 8 |  |  |  | 4 | 2 | 2 | 0.75 | 0.75 | 17.5
Feature 17 | 8 |  |  |  | 4 | 2 | 2 | 0.75 | 0.75 | 17.5
Feature 18 | 8 |  |  |  | 4 | 2 | 2 | 0.75 | 0.75 | 17.5
Feature 19 | 8 |  |  |  | 4 | 2 | 2 | 0.75 | 0.75 | 17.5
Feature 20 | 8 |  |  |  | 4 | 2 | 2 | 0.75 | 0.75 | 17.5
Total | 160 | 0 | 0 | 0 | 80 | 40 | 40 | 15 | 15 | 350
Tool Box
UI/UX/Designs | 50%
Delviery Lead | 25%
Account Lead | 25%
Tech Lead | 10%
Leadership | 10%
Summary | Effort (in hours) | Priority | Mandatory |  |  |  |  | Cost
Feature 1 | 17.5 | 1 | Y |  |  |  |  | 1362.5
Feature 2 | 17.5 | 2 | Y |  |  |  |  | 1362.5
Feature 3 | 17.5 |  | Y |  |  |  |  | 1362.5
Feature 4 | 17.5 |  | Y |  |  |  |  | 1362.5
Feature 5 | 17.5 |  | Y |  |  |  |  | 1362.5
Feature 6 | 17.5 |  | Y |  |  |  |  | 1362.5
Feature 7 | 17.5 |  | Y |  |  |  |  | 1362.5
Feature 8 | 17.5 |  | Y |  |  |  |  | 1362.5
Feature 9 | 17.5 |  | Y |  |  |  |  | 1362.5
Feature 10 | 17.5 |  | Y |  |  |  |  | 1362.5
Feature 11 | 17.5 |  | N |  |  |  |  | 1362.5
Feature 12 | 17.5 |  | N |  |  |  |  | 1362.5
Feature 13 | 17.5 |  | N |  |  |  |  | 1362.5
Feature 14 | 17.5 |  | N |  |  |  |  | 1362.5
Feature 15 | 17.5 |  | N |  |  |  |  | 1362.5
Feature 16 | 17.5 |  | N |  |  |  |  | 1362.5
Feature 17 | 17.5 |  | N |  |  |  |  | 1362.5
Feature 18 | 17.5 |  | N |  |  |  |  | 1362.5
Feature 19 | 17.5 |  | N |  |  |  |  | 1362.5
Feature 20 | 17.5 |  | N |  |  |  |  | 1362.5
Value Add (in Dollars) | 5000
Dollar already invested | 1000
Miscellaneous (in dollars) | 1000
Project costs with only mandatory items | 20625
Total Project Cost | 34250